## Big Block Plan
| SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT
| 2012 | 2012 | 2012 | 2012 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013
1000 Run Book Functionality
Andy
1100 VM within 15 minute Server
Rubin
1300 Employee Tracking
Jillian
1600 Credit Card Security
Harvey
1700 Limit Developer Access to production data
Harvey
1900 Document Code and Infrastructure
Harvey
1950 Document Schema
Harvey
2100 Accounting Systems
Jillian
2300 Development Road Map
Harvey
1010 Develop requirements with NOC
1020 Evaluate complexity of req and LOE to develop
1040 Look at commercial products
1050 Make develop/ purchase decision
1060 Implement and integrate
1070 Develop
1100 Define Products & determine market viability of products
1110 Determine technical ability to deliver going forward products
1120 Create Implementation Plan
1130 Implementation (if any)
1310 Review Cisco VOIP (owned, upgrade paths, etc)
1315 Select Phone System Path & investment
1320 Implementation/ Upgrade
1350 Drop IM Tracking & Corresponding Infrastructure
1355 Access Need/value of Windows Activity Tracking
1370 Review Web Sense configurations
1375 Refine Profiles for consistency
1380 Verify integrity of web sense reporting
1620 Understand PCI Spec
1640 Research Encryption tools
1650 Agree on design and tools
1660 Develop & Test
1710 Create Detect/Report change table/field list
1720 Create Prevent/lock down table/field list
1730 Create Ignore change table/field list
1740 Validate List and Approaches
1750 Develop/Enhance SQL level tracking of data element changes
1760 Remove user access to SQL tables (UI UX access only)
1770 Conduct formal audit of SQL access
1780 Narrow developer DB access / Implement lock downs
1910 Define what to document & Create Documentation standards
1915 Assign areas to staff, estimate resource impact/schedule
1920 Develop detailed infrastructure map
1925 Document assigned areas
1930 Validate/QC
1935 Begin Documentation Maintenance
1911 Establish Maintenance Plan for documentation
1955 Restore Production SQL to Test Environment
1960 Attempt Mapping, built in SQL tools
1965 Evaluate success of mapping
1970 Develop approach and plan to complete schema doc
1975 Complete/correct mapping (manual/tool based)
2110 Research & Select package (MS-Dynamics XXX)
2120 Develop functional architecture (what functions are run where?)
2130 Accounting Conversion
2105 Capture Proposal and Quote Generation requirements
2140 Develop UI UX integration
2150 Implement Quoting/Proposal generation
2310 Devise Roadmap format, process & performance metrics
2320 Put Things on Roadmap
2330 Institute policies for measurement of performance
2340 Establish Maintenance and revision process
1670 PCI Compliance Plan TBD
Leverage accounting system???
1075 Develop Plan for legacy customers
1610 Catalog impacted files and routines
1630 Develop a design
1670 Encryption in place
1080 Run Book Functionality in place
1790 Controls in Place
1980 Scheme Doc complete
2170 Accounting Systems Live
2350 Development Roadmap in place and functional

## Task Detail
Task |  |  |  | Responsible | Resource | Target Due | Next Step |  | Approved/ Complete | Notes
[7 empty] | Activity | Due Date
1000 Run Books |  |  |  | Andy
| 1010 | Develop requirements with NOC
|  | 1010.1 | Develop Draft format | Andy | Richard | 2012-11-11
| 1020 | Evaluate Complexity of requirements and development LOE |  | Andy | Harvey | 2012-11-30
| 1040 | Look at commercial products |  | Richard | Aaron | 2012-11-25 |  |  |  | as potential purchased solution or to inform requirements
1100 VM within 15 minute Server |  |  |  | Andy
1300 Employee Tracking |  |  |  | Jillian | [5 empty] | Drivers a) No failover between sites, b) HW long in tooth c) looking for new features
| 1310 | Review Cisco VoIP |  |  |  | 2012-11-15
|  | 1310.1 | Understand Current Cisco licensing and upgrade path | Jillian |  |  |  |  | 2012-10-08 | SmartNet agreement only provides for minor releases, expensive upgrade path
|  | 1310.2 | Look at Avaya as an alternative | Jillian |  | 2012-10-30
|  | 1310.3 | Look at Shoretel as an alternative | Jillian |  | 2012-10-30
|  | 1310.4 | Develop agreed upon phone systems features/requirements 5 year horizon | Jillian | Andy, Bob, Rubin | 2012-10-19
| 1315 | Select Phone System Path and Investment |  | Jillian |  | 2012-12-15
|  | 1315.1 | Set direction
|  | 1315.2 | Develop implementation plan
|  | 1315.3 | Design PRI and POTS line changes
| 1320 | Implement new phone systems
|  | 1320.1 | Design PRI and POTS line changes
| 1350 | Drop IM Tracking & Corresponding Infrastructure |  | Rubin
|  | 1350.1 | Identify IM tracking specific infrastructure - candidate for disco | Rubin | Jillian | 2012-11-01 | on track
|  | 1350.2 | Identify IM tracking related elements of UI UX to be remove | Lee |  | 2012-11-01 | on track
|  | 1350.3 | Turn off IM tracking and decommission infrastructure | Jillian | Erica, Lee | 2012-11-15 |  |  |  | Plan is to NOT RIP
| 1370 | Review WebSense configuration
|  | 1370.1 | Review WebSense configuration | Jillian |  | 2012-11-22 |  |  | 2012-09-30 | Single profile except (Bob, Rubin & Jillian), some one off user exceptions for website monitoring in NOC. No tracking or restriction on wireless
|  | 1370.1 | Look into alternative of either adding wireless to websense | Steve-O |  | 2012-11-05 | on track
|  | 1370.2 | Institute regular review of websense reports | Jillian |  | 2012-11-01
| 1375 | Develop written HR policy about circumventing WebSense, Smartphone surfing and reporting review |  | Jillian |  | 2012-11-22
| 1380 | Verify integrity of WebSense reporting |  | Jillian |  | 2012-12-27 |  |  |  | Q: can reporting DB be deleted or pruned
1600 Credit Card Security |  |  |  | Harvey
| 1610 | Catalog tables and routines affected |  | Harvey | Rex R | 2012-11-15 | Finalize 80% complete | 2012-11-01 |  | - looking for tables where any of the 4 cc elements are stored, looking for routine that handle any of the 4 cc elements - most touchpoint Id'ed in design 1630.20 - Charge, Refunds, Chargebacks
| 1620 | Understand PCI Spec |  | Harvey | Jillian, Richard | 2012-10-17 | Final | 2012-10-17 | 2012-10-18
| 1630 | Develop a Design |  | Harvey |  | 2012-12-05
|  | 1630.1 | Write project scope statement | Harvey | Richard | 2012-11-01 | Publish to team | 2012-11-01 |  | Goal is to improve the security of cc storage and handling using PCI as a guideline, not achieving PCI certification. Decision: No SSL for transmission
|  | 1630.2 | Develop high-level design | Harvey | Richard | 2012-11-15 |  |  | 2012-10-23 | Encryption, keys, storage
|  | 1630.3 | First review scope, design & level of protection | Harvey | Team | 2012-11-16 |  |  | 2012-10-23
|  | 1630.4 | Revisions based on feedback | Harvey | Richard | 2012-11-30 |  |  | 2012-10-23 | previous cycles - Tuesday meetings
|  | 1630.5 | Final approval on scope, design & level of protection | Harvey | Rubin | 2012-12-05 |  |  | 2012-10-23 | Completed in Design
| 1640 | Research and select Encryption tools (and Hash Index) |  | Harvey |  | 2012-12-15 |  |  | 2012-10-23 | Completed in Design
| 1650 | Sign off on scope, design and implementation approach (1660) |  | Harvey | Erica, Lee | 2012-12-15 | Final | 2012-11-02
| 1655 | Validate decision on history - last 4 cc, type, no expire, no CVV |  | Harvey | Erica, Lee |  | Final | 2012-11-02 |  | effects 250,000 records and going forward
| 1657 | Identify all back-up, production and non-production copies of cc data, develop plan for each |  | Harvey |  | 2012-11-15
| 1670 | Implementation Approach (Develop and test) |  | Harvey | Team
|  | 1670.1 | Verify POC in production instance | Harvey | Ryan | 2012-11-05
|  | 1670.2 | Brief accounting on project and potential impact of go live | Harvey | Paul | 2012-11-05
|  | 1670.3 | Develop and unit test code that runs cards to use encrypted cc and new functions for Charge Type = "Encrypted CC" | Harvey | Ryan or Lee | 2012-11-09 |  |  |  | includes storing history per design
|  | 1670.4 | Update TBL ENTITIES and create new encrypted CC field retain free text CC |  |  | 2012-11-09
|  | 1670.5 | Add value to TBL ENTITIES - Charge Type: "Encrypted CC" |  |  | 2012-11-09
| 1675 | System Testing
|  | 1675.1 | Change Charge Type to "Encrypted CC" for test entities (employees) |  |  | 2012-11-14
|  | 1675.2 | Validate proper cc charges for tests |  |  | 2012-11-14
| 1680 | Go Live
|  | 1680.1 | Change Charge Type to "Encrypted CC" for dial-up and email customers |  |  | 2012-11-27
|  | 1680.2 | Validate proper cc charges for tests |  |  | 2012-11-27
|  | 1680.3 | Change Charge Type to "Encrypted CC" for balance of customers |  |  | 2012-12-11
|  | 1680.4 | Validate proper cc charges for tests |  |  | 2012-12-11
| 1685 | Clean-up/Wrap-up
|  | 1685.1 | Update 250,000 records of processed cards per history design |  |  | 2012-01-15
|  | 1685.2 | Update TBL ENTITIES replace CC free text with 4 digit masked |  |  | 2012-01-15
|  | 1685.3 | Disable cc search in UI UX |  |  | 2012-01-15
|  | 1685.4 | Execute plan for back-up data copies |  |  | 2012-01-15
| 1685 | Milestone: Encryption in place |  | Harvey | Team | 2013-01-31
| 1690 | Evaluate adding SSL encryption on UI UX <=> SQL transmissions
1700 Limit Developer Access to production data |  |  |  | Harvey
1900 Document Code and Infrastructure |  |  |  | Harvey
1950 Document Schema |  |  |  | Harvey
2100 Accounting Systems |  |  |  | Jillian
| 2120 | Develop functional systems architecture
|  | 2120.1 | Plan architecture workshop | Richard | [5 empty] | Jillian, Aaron, Scott, UI UX Person (Steve/Lee/Ryan), 10/23 PM & 10/24 AM
|  | 2120.2 | Conduct workshop prep call | Jillian | Richard | 2012-10-11 |  |  |  | Goals what people need to prepare, straw man
|  | 2120.3 | Develop draft target architecture in workshop |  |  | 10/23 & 10/24
|  | 2120.4 | Present & refine target architecture |  |  | 2012-11-15
2300 Development Road Map |  |  |  | Harvey